## Sheet1
Sprint Plan #1
Game: Bubble Beam
Group: Group-12
User Story | Task | Task Assigned To | Estimated Effort per Task*
| Write Write tests fors for BubbleMesh | Liam | 2
| Write tests for ColouredBubble | Leon | 1
| Write tests for Cannon | Sam | 2
| Write tests for MovingBubble | Luka | 1
| Write tests for ObservableObject | Liam | 1
| Write tests for Vector2f | Luka | 1
| Assigment 1.1 | Jan-Willem | 2
| Assigment 1.2 | Jan-Willem | 2
| Assigment 1.3 | Sam | 1
| Assigment 1.4 | Leon | 3
| Assigment 2.1 | Luka | 2
| Assigment 2.2 | Sam | 1
| Assigment 2.3 | Liam | 2
| Comments – Bubble** | Liam | 2
| Comments – Cannon | Sam | 1
| Comments – MovingBubble | Luka | 1
| Comments – GameOver | Liam | 1
| Comments – GUI | Leon | 1
| Comments – Launcher | Sam | 1
| Comments – GuiThrowAwayPanel | Leon | 1
| Comments – ObservableObject | Liam | 1
| Comments – Vector2f | Luka | 1
Assigment 3 | Assigment 3.2 – Planning | Sam & Luka & Leon | 3
The game has to allow at least two players playing using two computers connected through the network. | Setting up connection | Sam & Luka | 3
| Bubble shooting sync | Sam & Luka | 3
| Bubble popping sync | Sam & Luka | 3
| Level sync | Sam & Luka | 3
| GUI for multiplayer | Leon | 3
When bubbles pop, then bubbles should appear on the opponent's side. | inplement mechanic | Leon | 3
| Fix – Game-over bug | Jan-Willem | 2
| Fix – Rename GuiThrowAwayPanel | Leon | 0
| Fix - Bubble popping bug | Jan-Willem | 1
*The estimated effort per task is scored from 0 to 3, with 0 being no effort and 3 being moderate effort
**:AbstractBubble, Bubble, BubbleMesh, BubblePlaceholder, ColouredBubble